## 1. Instructions
Urb TecTrack™ — Client Portal UAT Checklist
For testers with Client access only · Capture results in this workbook and return to Urbeno
Document version | 1.0
Audience | Client portal users (requestors) — not Urbeno staff
Purpose | Validate client-facing features before production / go-live sign-off
How to use | 1) Fill Environment on sheet 2. 2) Execute cases on sheet 3. 3) Mark Result for every row. 4) Complete Sign-off on sheet 4.
Result values | Pass = works as expected · Fail = defect · N/A = not applicable this round · Blocked = cannot run (dependency / environment)
Nav expected | Home · My Requests · Recycling Heroes · Sustainability · Reports (no Masters, Audit, Capacity, or Compliance)
Demo accounts (UAT environments)
Organisation | Email | Name | Password | Notes
TechCorp Pvt Ltd (TCPL) | ramesh@techcorp.in | Ramesh Kumar | demo | Primary client tester
TechCorp Pvt Ltd (TCPL) | priya@techcorp.in | Priya Sharma | demo | Second TechCorp user
Bharat Retail (BHRT) | anand@bharatretail.in | Anand Desai | demo | Alternate client org
Infosoft (INFR) | meera@infosoft.in | Meera Iyer | demo | Use for tenancy negative checks
Important rules for client testers
• | You only see your own organisation’s requests, certificates, and reports.
• | You cannot create MRNs, issue Form 6, or upload Certificates of Destruction — those are Urbeno / factory steps.
• | Review & Close is only available after the Certificate of Destruction is on file and the invoice is fully paid.
• | Sustainability and Recycling Heroes figures count closed invoices only.
• | If a policy gate appears after login, open each policy and accept before continuing.
• | Do not change the shared demo password unless you are the last tester of the day.
Support | Raise issues in the request Query thread or email your Urbeno UAT contact. Attach screenshots for Fail / Blocked cases.

## 2. Environment
Test environment & tester details
Field | Value | Notes
Environment URL |  | e.g. https://uat.urbeno.in or http://localhost:8080
Build / release / git SHA
Tester full name
Tester organisation
Tester email
Account used for this run | demo | unless this environment rotated it
Password used | 2026-08-21
Test date (IST) |  | e.g. Chrome on macOS / Edge on Windows
Browser / device |  | Optional — from cross-role lifecycle script
Shared lifecycle request ID (if any) | REQ-__________
Urbeno UAT contact

## 3. Test Cases
Client portal test cases — mark Result for every row
Section | ID | Test step | Expected result | Result | Actual result / evidence | Severity (if Fail) | Tester initials | Date | Notes
C0 Sign-in & shell | C0.1 | Open the portal URL while signed out. | Login screen is shown. Enter your client email (not a pre-filled staff email) and password. |  |  | High
C0 Sign-in & shell | C0.2 | Sign in. If “Accept policies” appears, open each policy link, then accept. | Policy gate clears. Home shows Welcome, <first name>. Subtitle shows Client portal. |  |  | High
C0 Sign-in & shell | C0.3 | Check the main navigation. | Only: Home, My Requests, Recycling Heroes, Sustainability, Reports. No Masters, Audit, Capacity, Compliance. |  |  | High
C0 Sign-in & shell | C0.4 | Open profile (avatar / name chip). | Role = Client. Organisation ID shown. Change-password (and MFA if offered) are available. |  |  | Medium
C0 Sign-in & shell | C0.5 | Logout, then sign in again. | Returns to Home. Policies are not re-prompted unless a new version was published. |  |  | Medium
C1 Tenancy & access | C1.1 | Open My Requests and scan the list. | Only your organisation’s requests appear. No other client’s request IDs. |  |  | Critical
C1 Tenancy & access | C1.2 | In the address bar open another organisation’s request URL (ask Urbeno for a foreign REQ- id, e.g. from Infosoft). | Access refused or redirected. Must not show another client’s site / details. |  |  | Critical
C1 Tenancy & access | C1.3 | Open Reports and review available report types. | Own-org data only. MRN Register is NOT listed (internal to Urbeno). |  |  | High
C1 Tenancy & access | C1.4 | Try direct URLs: /masters, /audit, /compliance, /capacity. | Redirected to Home or not found. No staff master/audit/compliance screens. |  |  | Critical
C2 New request | C2.1 | Home → + New Request (or My Requests → new). | New Collection Request form. Client organisation is implied (no client picker). Site is required. |  |  | High
C2 New request | C2.2 | Submit with required fields empty. | Form stays open with validation errors (site, location, date, qty/weight and/or line items). |  |  | Medium
C2 New request | C2.3 | Complete Pickup Location, approx weight & qty, at least one line item (optional PO/ref/notes/BoM). Submit. | Request detail opens with new REQ-#####. Stage = 1 (awaiting Urbeno acknowledgement). |  |  | Critical
C2 New request | C2.4 | Confirm header on the new request. | Shows your client, site, request date, Raised By = you. No staff actions (Acknowledge, Assign Vehicle, Raise Invoice, Upload Certificate). |  |  | High
C3 Changes requested | C3.1 | After Urbeno sends the request back with changes: open it. | Badge/card shows Changes requested with Urbeno’s note. (Mark N/A if not run this cycle.) |  |  | Medium
C3 Changes requested | C3.2 | Edit pickup location (or other field) and Save / resubmit. | Confirmation that request was sent back to Urbeno. Still stage 1. Client cannot Acknowledge. |  |  | Medium
C4 Ops visibility | C4.1 | On an in-progress request, refresh after staff progress (vehicle / weigh / invoice). | Stage badge advances. Vehicle registration and invoice number are visible when present. |  |  | High
C4 Ops visibility | C4.2 | Inspect invoice / receiving area. | No MRN number, no Create MRN, no factory security-officer fields. |  |  | Critical
C4 Ops visibility | C4.3 | After recycling / Form 6 is issued by Urbeno. | You can see that processing occurred / Form 6 is available to download. You are not asked to issue Form 6. |  |  | High
C4 Ops visibility | C4.4 | After Certificate of Destruction is uploaded by Urbeno. | Certificate number and date visible. Download works. Upload Certificate is NOT available to you. |  |  | Critical
C4 Ops visibility | C4.5 | Before the invoice is fully paid, check Review & Close. | Review & Close is absent or closing is refused until payment is complete. Home does not show a false “ready to close” prompt for unpaid invoices. |  |  | High
C5 Close request | C5.1 | When CoD exists AND invoice is paid: open Review & Close. | Modal / flow to acknowledge closure is available. Download CoD if you want to review first. |  |  | Critical
C5 Close request | C5.2 | Acknowledge closure (optional rating/note). | Invoice/request closes successfully. Stage shows Closed. |  |  | Critical
C5 Close request | C5.3 | Return to Home. | Completed count increased. Open count decreased accordingly. |  |  | Medium
C6 Home & impact | C6.1 | Open Home. | Tiles: open requests, completed, recycled kg, trees. Quick links to Requests / Sustainability / Heroes / Reports. + New Request visible. Site filter chips work if multiple sites. |  |  | High
C6 Home & impact | C6.2 | Open Sustainability. | Shows closed-lifecycle impact (kg, CO₂e, landfill, etc.). “How these numbers are built” and Impact PDF open successfully. |  |  | High
C6 Home & impact | C6.3 | Open Recycling Heroes. | Shows your organisation’s trees / tonnage. Methodology link works. Record any CSR planting button behaviour you see. |  |  | Medium
C7 Reports & downloads | C7.1 | Reports → Request Summary (or Invoice Register) → Export CSV. | CSV downloads. Contains only your organisation’s rows. |  |  | High
C7 Reports & downloads | C7.2 | Reports → Certificate Log. | Rows list certificates. Each row has ⬇ Download where a file exists. Export PDF/CSV works. |  |  | Critical
C7 Reports & downloads | C7.3 | Reports → Form 6 Log → Export PDF (and/or open a Form 6 from a request). | PDF opens/downloads without error for your org’s data. |  |  | High
C7 Reports & downloads | C7.4 | Change reporting period (FY / calendar / custom) if shown. | Figures/rows refresh. Still no other client’s data. Still no MRN register. |  |  | Medium
C7 Reports & downloads | C7.5 | On a request with CoD: use ⬇ Download on Certificate of Destruction / Compliance Documents. | Certificate PDF opens. Label is clear (Download), not a blank icon. |  |  | Critical
C8 Notifications & search | C8.1 | Open the notification bell. | Panel lists notifications. Unread count makes sense. Marking read (if available) works. |  |  | Low
C8 Notifications & search | C8.2 | Use global search with a known REQ- id from your org. | Request appears in results and opens correctly. |  |  | Medium
C9 Profile (optional) | C9.1 | Profile → change password to something too short (e.g. “short”). | Rejected. Password policy message shown (length / complexity). |  |  | Low
C9 Profile (optional) | C9.2 | Skip a real password change on the shared demo user unless you are the last tester. | N/A is acceptable for shared UAT accounts. |  |  | Low
C10 Queries | C10.1 | On one of your requests, post a query / message to Urbeno. | Message is saved and visible in the thread. |  |  | Medium
Result legend: | Pass | Fail | N/A | Blocked
Tip: Filter the Result column to find open Fail/Blocked items before sign-off.

## 4. Sign-off
Client UAT sign-off
Summary tallies (auto-calculated from sheet 3)
Metric | Count
Total cases
Pass
Fail
N/A
Blocked
Not yet marked
Overall assessment
Fit for production as a Client portal user? |  | Select from dropdown
Blockers / waiver IDs
Key observations
I confirm I executed this client UAT script on the environment named on sheet 2 and that the results are accurate.
Role | Name | Organisation | Signature / email confirmation | Date
Tester
Client sponsor (optional)
Urbeno UAT lead (optional)

## 5. Defect Log
Defect / issue log (optional — one row per Fail or Blocked)
Defect # | Linked case ID | Summary | Steps to reproduce | Expected | Actual | Severity | Status | Owner | Resolution / date