URBENO PRIVATE LIMITED

Recycling Heroes™

URB TECTRACK™

Backend Production Build Plan

Taking the working prototype to a hosted, multi-tenant, audit-ready platform

| Document | Purpose | Audience |
| --- | --- | --- |
| Build Plan v1 | Phase-by-phase engineering plan for production delivery | Development partner, Urbeno technical owner |

| Reference input | What it provides |
| --- | --- |
| urb-tectrack-v6.3-complete.html | The working prototype. Authoritative for business rules, screens and data shape. |
| Urbeno-TecTrack-RFP-v3.docx | Commercial scope, workstreams, non-functional requirements. |
| Authorization_break_up_Urbeno.xlsx | 126 authorised category entries per facility. |
| Urbeno-Sustainability-Methodology.pdf | How every environmental figure is derived. |

CONFIDENTIAL

# How to read this plan

This document turns the Urb TecTrack prototype into a production build sequence. It is written for the engineering team that will do the work and for the Urbeno owner who has to judge whether a phase is genuinely finished.

Twelve phases run roughly in order, though several overlap. Each phase states what it delivers, the work inside it, the decisions that must be settled before it starts, and — most importantly — the exit criteria. The exit criteria are the point of the document. A phase is not complete because the code exists; it is complete when someone can demonstrate the listed conditions.

The one rule that matters most

The prototype already separates business logic from storage. Every mutation flows through a service object — db.subs, db.inv, db.veh, auth, audit, notify, mail, files, catm — and each carries a // MIGRATION: comment marking the exact swap point. There are seventeen of these markers.

Do not rewrite the business rules. Port them. The prototype encodes rules that took several rounds of operational feedback to get right: category splits must reconcile to invoice weight, MRN sequences reset each April per facility, closure requires full payment, stage is derived rather than stored. Rewriting from a specification will lose these. Reading the prototype and replacing only the storage layer will not.

A note on estimates Durations assume a team of two senior full-stack engineers, one mid-level engineer, a part-time DevOps engineer and a part-time QA engineer, as set out in the RFP. A smaller team does not compress these phases; it extends them. The total sits at 14 to 16 weeks. Phases 0 and 1 look administrative and are routinely underestimated — the accounts, domains and legal groundwork in Phase 0 have long lead times and should start on day one.

# The phases at a glance

| # | Phase | Weeks | Delivers |
| --- | --- | --- | --- |
| 0 | Decisions and prerequisites | W1 | Stack fixed, accounts open, legal started |
| 1 | Foundation and environments | W1–2 | Repo, CI/CD, three environments, schema |
| 2 | Identity, tenancy and access | W2–4 | Login, roles, row-level isolation, reset |
| 3 | Core domain API | W3–7 | The nine-stage lifecycle as real endpoints |
| 4 | Documents and file storage | W5–8 | S3, server-side PDFs, retention |
| 5 | Notifications and email | W6–9 | Transactional mail, templates, campaigns |
| 6 | Frontend migration | W5–10 | Prototype UI wired to the API |
| 7 | Scheduled work | W8–10 | Payment reminders, SLA watch, alerts |
| 8 | Reporting and analytics | W9–12 | Eight reports, exports, dashboards |
| 9 | Security hardening and DPDPA | W10–13 | Audit, pen test, compliance posture |
| 10 | Data migration and UAT | W12–14 | Real data loaded, ops team signed off |
| 11 | Go-live | W14–15 | Production cutover |
| 12 | Operate and hand over | W15–16+ | Runbook, monitoring, warranty |

Phases 3 and 6 are the bulk of the work and run in parallel once the API contract is agreed. Phase 9 must not be compressed; it is the phase most often sacrificed to a deadline and the most expensive to skip.

| PHASE 0 | Decisions and prerequisites | DURATION Week 1 | LEAD Urbeno + Lead |
| --- | --- | --- | --- |

Nothing here is code. All of it blocks something later, and several items have lead times measured in weeks, so start on day one.

Decisions Urbeno must make

- Hosting region — Must be in India. AWS ap-south-1 (Mumbai) or Azure Central India. This is a data-residency commitment, not a preference.

- Managed vs self-hosted database — Managed Postgres (RDS, Azure Database, or Supabase) removes a standing operational burden. Recommended unless there is a specific reason not to.

- Domain — A subdomain such as tectrack.urbeno.in. Decide now; DNS and certificates depend on it.

- Email sending domain — Transactional mail must send from a domain Urbeno controls, with SPF, DKIM and DMARC. Warming a new sending domain takes two to three weeks — start immediately.

- Email service provider — SendGrid, Amazon SES or Zoho ZeptoMail. SES is cheapest and has the most setup friction.

- WhatsApp business service provider — Gupshup, AiSensy or Twilio. Template approval by Meta takes one to two weeks.

- Backup retention — Thirty days of daily backups is the baseline. Confirm whether any client contract demands more.

Accounts and access to open

- Cloud account with billing alerts configured and a separate production account or subscription

- Source control organisation owned by Urbeno, not by the development partner

- Error tracking (Sentry or equivalent), uptime monitoring, and a status page if clients will be given one

- Email, SMS and WhatsApp provider accounts, with sender identities verified

- A shared password manager for the credentials above — no secrets in chat or email

Legal and compliance, started now

- Privacy policy and terms of service reviewed against the DPDPA. The prototype already contains a Terms of Use document; it is a starting draft, not legal advice, and must be reviewed by counsel.

- Data processing agreement between Urbeno and the development partner

- Mutual NDA if not already signed

- Book the third-party security audit for Phase 9 now — good firms are booked four to six weeks out

Technical decisions the partner must record

- Language and framework, with the reasoning written down

- API style — REST or GraphQL. REST is recommended here; the prototype service layer maps to resource endpoints almost one to one.

- Migration tooling, so schema changes are versioned from the first commit

- Test framework and the coverage bar the team will hold itself to

Exit criteria — do not start the next phase until all of these are true ☐ Hosting region, database choice and domain are decided and recorded ☐ All cloud, email, SMS and monitoring accounts exist and are owned by Urbeno ☐ Sending domain is configured with SPF, DKIM and DMARC and is warming ☐ Security audit is booked with a date ☐ Counsel has the privacy policy and terms in hand ☐ A one-page architecture decision record exists and Urbeno has read it

| PHASE 1 | Foundation and environments | DURATION Weeks 1–2 | LEAD Partner |
| --- | --- | --- | --- |

The aim is a repository where an empty feature can travel from a developer laptop to production through automation, before any real feature exists. Teams that defer this end up deploying by hand for months.

Repository and pipeline

- One repository, Urbeno-owned, with branch protection on main

- Continuous integration on every push: linting, type checking, unit tests, and a build

- Continuous deployment to development on merge, to staging on tag, to production on manual approval

- Secrets held in the platform secret store, never in the repository

Three environments

- Development — Seeded with the prototype demo data. Wiped and reseeded freely. Engineers work here.

- Staging — Production-shaped. Real schema, anonymised data, every third-party service in test mode. UAT happens here.

- Production — Real data. Access restricted. Deploys require approval and are logged.

Database schema

Model the entities the prototype already defines. The full inventory sits in Appendix B of RFP v3; the shape below is what the prototype actually carries.

| Table | Notes that matter |
| --- | --- |
| clients | Four-character uppercase code as the business key, immutable once created. Payment terms live here. |
| sites | Per-client. Own GSTIN, address and pickup contact. Deactivate, never delete, once referenced. |
| factory_sites | Urbeno facilities. Own GSTIN, KSPCB consent, CPCB/EPR number, and MRN sequence state. |
| users | Role of admin, factory or client. Site and factory scoping arrays. |
| category_master | 252 rows — 126 authorised entries replicated per facility. Capacity in tonnes per annum. |
| submissions | The request. Stage is derived, not stored — see Phase 3. |
| vehicles | Many per submission. Carries the manual-weighment flag. |
| vehicle_team | Many per vehicle. Name, role, phone for every person. |
| weighments | One per vehicle. Gross, tare, net, or a manual figure with method and reason. |
| invoices | Many per submission. Own e-way bill, tax rate, billing weight, deviation note. |
| payments | Many per invoice. |
| mrns | One per invoice. Factory-scoped, fiscal-year sequenced number. |
| recycling | One per invoice. Form 6 number, processing date, facility. |
| recycling_categories | The category split. Each row carries its own material recovery. |
| serials | Device-level chain of custody with destruction record. |
| certificates | Many per invoice. Certificate number unique across the whole system. |
| files | Metadata only. Bytes live in object storage. |
| tree_plantings | Recycle Heroes ledger, with dated growth photographs. |
| email_templates | Fixed transactional templates plus admin-editable ones. |
| audit_log | Append-only. Seven-year retention. |
| notifications | Per user, in-app. |

Two schema decisions worth getting right on day one Money as integer paise, never floating point. The prototype uses JavaScript numbers because it is a prototype; production must not. Weights as numeric with two decimal places. Weighbridge tickets are quoted to the kilogram and reconciliation depends on exact arithmetic.

Seed and reference data

- Load all 252 category master rows from the authorisation spreadsheet, tagged by facility

- Load the lookup masters: logistics partners with GSTIN, vehicle types, team roles, payment modes, payment terms, tax rates, HSN codes, sanitisation standards

- Load the fixed transactional email templates verbatim from the prototype

- Keep the seed script in the repository — it is how a new environment gets built

Exit criteria — do not start the next phase until all of these are true ☐ A trivial change reaches production through the pipeline with no manual step ☐ All three environments exist and are reachable at their own URLs ☐ Schema is created by a versioned migration, not by hand ☐ Seed script populates the 252 category rows and every lookup master ☐ Rolling back one migration and reapplying it works ☐ A restored backup produces a working database

| PHASE 2 | Identity, tenancy and access | DURATION Weeks 2–4 | LEAD Partner |
| --- | --- | --- | --- |

Every later phase depends on knowing who is asking and what they may see. Build it once, properly, and enforce it in one place.

Authentication

- Password hashing with bcrypt or argon2. The prototype uses SHA-256 and says so in a comment — that is demo-grade and must not survive.

- Server-side sessions in HttpOnly, Secure, SameSite cookies, or JWT with refresh rotation

- Thirty-minute idle timeout with a five-minute warning, matching the prototype

- Account lockout after five failed attempts within fifteen minutes

- TOTP multi-factor, mandatory for admin and factory roles, optional for clients

Password reset

The prototype implements the flow already: a six-digit code, valid fifteen minutes, single use, delivered by email.

- Rate limit to five requests per email per fifteen minutes

- Respond identically whether or not the account exists, so the endpoint cannot be used to discover users

- Invalidate every existing session on a successful reset

- Store the code hashed, never in plain text

Roles and scoping

| Role | Sees | Notes |
| --- | --- | --- |
| admin | Everything | Full lifecycle, masters, audit, email |
| factory | All requests, scoped to their facilities | MRN and recycling stages; no billing |
| client | Own organisation only, optionally one site | Never sees MRNs — this is deliberate |

Tenant isolation is not a filter in a query Enforce it at the database with row-level security, or in a single middleware layer that every query passes through. A WHERE clause added per endpoint will eventually be forgotten on one endpoint, and that is a client seeing another client's data. The test that matters: sign in as a client and request another client's submission by its identifier directly. The answer must be a 404, not a 403 — a 403 confirms the record exists.

Audit from the first endpoint

The audit log is append-only and retained seven years. Wire it in Phase 2, not later — retrofitting audit coverage means auditing your own gaps.

- Every mutation writes actor, action, entity, entity identifier, timestamp and a before/after payload

- Authentication events included: login, failure, lockout, reset request, reset completion, password change

- No update or delete permission on the table for the application role

Exit criteria — do not start the next phase until all of these are true ☐ A client user cannot reach another client's data by identifier, and the attempt is logged ☐ A site-scoped user sees only their site in every list, aggregate and report ☐ A factory user can reach MRN and recycling but not billing ☐ Password reset works end to end and invalidates other sessions ☐ MFA enrolment and challenge work for an admin account ☐ Lockout triggers and expires correctly ☐ Every mutation so far appears in the audit log with before and after values

| PHASE 3 | Core domain API | DURATION Weeks 3–7 | LEAD Partner |
| --- | --- | --- | --- |

The heart of the build. Port the prototype service layer to real endpoints, preserving behaviour exactly. Work stage by stage, in lifecycle order, so there is always something demonstrable.

Method for this phase

- Open the prototype, find the service method, read it including its validation and its error messages

- Write the endpoint, then write tests that assert the same rules — including the refusals

- Port the error text as well. It was written to tell an operator what to do next, and rewriting it as "Validation failed" removes the value.

The nine stages

| Stage | Endpoint area | The rules that must survive |
| --- | --- | --- |
| 1 Request | POST /submissions | Client or admin-on-behalf. Approximate weight and quantity. Bill of materials upload. Notifies admins by email. |
| 2 Acknowledge | POST /submissions/:id/acknowledge | Admin only. Fires the acknowledgement email. Rejection returns it to the client with a reason. |
| 3 Assign vehicles | POST /submissions/:id/vehicles | Many vehicles. Each carries a team, and every team member needs a name, role and phone. |
| 4 Weigh | POST /vehicles/:id/weighment | Gross must exceed tare. Slip number and at least one slip photo and one pickup photo. Manual mode skips gross, tare and slip but demands a recorded weight, a method and a written reason — and still a pickup photo. |
| 5 Billing | POST /submissions/:id/invoices | Many invoices. Each needs its own e-way bill number and PDF. Tax rate chosen from the master; tax value and total are derived, never submitted. Billing weight defaults to the weighed vehicle net; any difference requires a deviation note. |
| 6 MRN | POST /invoices/:id/mrn | One per invoice. Factory manager only. Number generated as MRN/[Facility]/[FY]/[sequence], resetting each April, per facility. No category split at this stage — it is a gate document. |
| 7 Recycling | POST /invoices/:id/recycling | Category split must total the invoice billing weight exactly. Each category carries its own material recovery, which must reconcile to that category's weight. Capacity checked against the facility's authorisation; exceeding it requires an override with a reason, and the override is logged. |
| 8 Certificate | POST /invoices/:id/certificates | Many per invoice, each with an optional department. Certificate number unique system-wide. Upload emails the client with the PDF attached. |
| 9 Close | POST /invoices/:id/close | Requestor only, or any client user after thirty days. Requires a certificate and full payment. Admin force-close permitted after sixty days with a reason. |

Three rules that are easy to get wrong

These caused real defects during prototype development. Each deserves its own test.

Stage is derived, never stored

A stage counter drifts. Imported records, hand edits and older code all leave it behind the actual paperwork, and the result is a dashboard that disagrees with the request when you open it. That defect occurred and was fixed by deriving stage from the records themselves.

invoice stage: has closure -> 9 Closed has any certificate -> 8 Certificate has recycling record -> 7 Recycling has MRN -> 6 MRN otherwise -> 5 Billing submission stage = the LEAST advanced of its invoices (a request is only as finished as its slowest invoice)

Compute this in the database as a view or generated column, or in one shared function on the server. If a stored counter is kept as a cache, add a reconciliation job that repairs and logs drift.

MRN numbering must be atomic

Two receipts at the same facility at the same moment must not collide, and the sequence must not skip. A read-then-write in application code will eventually produce a duplicate or a gap under load.

Format: MRN/URB-KGF/2627/0001 facility code, fiscal year (Apr-Mar), 4-digit sequence Allocate inside a transaction, using either a) SELECT ... FOR UPDATE on a per-facility-per-year counter row, or b) a Postgres sequence created per facility per fiscal year Never generate the number in application code before the transaction.

Ask the vendor how they will do this. It is question 4 in the RFP for a reason — the answer reveals whether they think about concurrency.

Financial year is April to March

It governs MRN sequences, capacity utilisation, reports and Recycle Heroes. Write one date helper and use it everywhere. A March date belongs to the year that started the previous April.

Capacity enforcement

- Utilisation is measured per facility, against that facility's own 126 authorised entries

- Warn at eighty per cent, block at one hundred per cent unless overridden

- An override requires a reason and writes an audit entry — this is the record that matters if CPCB asks

Exit criteria — do not start the next phase until all of these are true ☐ All nine stages work end to end through the API for a multi-invoice request ☐ Every validation refusal in the prototype has a matching test that asserts the refusal ☐ Stage is derived; a record with a deliberately corrupted counter still reports correctly ☐ Concurrent MRN creation at one facility produces no duplicates and no gaps under a load test ☐ Fiscal year boundaries are correct at 31 March and 1 April ☐ Capacity override is possible, requires a reason, and is audited ☐ Closure is refused without payment, and without a certificate

| PHASE 4 | Documents and file storage | DURATION Weeks 5–8 | LEAD Partner |
| --- | --- | --- | --- |

The prototype stores files inline as data URIs, which is why it caps them at a few megabytes. Production moves bytes to object storage and keeps only metadata in the database.

Object storage

- S3, Cloudflare R2 or equivalent, in the Indian region

- Uploads go direct from browser to storage using a pre-signed URL — never stream large files through the API

- Downloads issued as short-lived pre-signed URLs after an authorisation check

- Bucket private by default. A public bucket here would expose client compliance documents.

- Virus scanning on upload

- Server-side encryption at rest

What gets uploaded, and the limits

| Stage | File | Limit | Required |
| --- | --- | --- | --- |
| 1 Request | Bill of materials (CSV, Excel, PDF) | 10 MB | Optional |
| 4 Weigh | Weighment slip photos | 5 MB each | At least one, unless manual |
| 4 Weigh | Pickup photos | 5 MB each | At least one, always |
| 5 Billing | Invoice PDF | 10 MB | Yes |
| 5 Billing | E-way bill PDF | 10 MB | Yes |
| 7 Recycling | Serial import CSV | 5 MB | Optional |
| 7 Recycling | Processing photos and reports | 5 MB each | Optional |
| 8 Certificate | Certificate PDF | 5 MB | Yes |
| Masters | Client logo | 2 MB | Optional |
| Heroes | Planting and growth photographs | 5 MB each | Optional |

Server-side PDF generation

The prototype generates PDFs in the browser with jsPDF. That is fine for a prototype and wrong for production: documents must be reproducible, identical for every user, and generatable by a background job.

- Move generation to the server, using Puppeteer with HTML templates or a PDF library

- Documents to produce: MRN, Form 6, sustainability certificate, methodology, and every report export

- Store generated documents rather than regenerating on each request, so a downloaded document never changes after the fact

- Match the prototype layouts — they have been reviewed and the MRN in particular is a signed gate document

The MRN is a physical document It is printed, signed by the driver, the factory manager and security, and filed at the gate. It must fit one A4 page, print legibly in black and white, and carry all three signature blocks. Verify by printing it, not by looking at it on screen.

Retention

- Compliance records — Form 6, MRN, manifests — five years minimum, per Rule 12(4)

- Certificates of destruction — ten years

- Audit log — seven years

- Implement retention as lifecycle policy plus a deletion job, and log what is deleted

Exit criteria — do not start the next phase until all of these are true ☐ A 10 MB upload succeeds without passing through the API server ☐ A file cannot be downloaded by a user from another client, even with the direct URL ☐ MRN and Form 6 generate server-side and match the prototype layout ☐ A printed MRN is legible and fits one page with all three signature blocks ☐ Retention policy is configured and a dry run reports what it would delete

| PHASE 5 | Notifications and email | DURATION Weeks 6–9 | LEAD Partner |
| --- | --- | --- | --- |

Two tiers, already modelled in the prototype: fixed transactional templates that fire automatically and cannot be edited, and admin-editable templates for client communications.

Fixed transactional templates

| Template | Fires when |
| --- | --- |
| New request received | A client submits a request — goes to Urbeno admins |
| Request acknowledgement | Admin accepts the request — goes to the requestor |
| Certificate delivery | A certificate is uploaded — with the PDF attached |
| Payment reminder | Daily sweep finds an overdue invoice |
| Recycling SLA alert | An invoice approaches or breaches the thirty-day target |
| Password reset code | A user requests a reset |
| New user welcome | An admin creates a user |
| Capacity alert | A category crosses eighty or one hundred per cent |

Delivery infrastructure

- Send asynchronously through a queue — never block an API response on an email

- Retry with exponential backoff, and a dead-letter queue for repeated failures

- Record every send in an outbox the admin can search, as the prototype does

- Handle bounces and complaints, and suppress addresses that hard-bounce

- Attachments pulled from object storage at send time

Admin-editable templates and campaigns

- Rich text editor with a merge-variable palette

- Recipient targeting: all clients, primary contacts, one client, or a test send to self

- Preview with sample data, and a test send before a campaign goes out

- Delivery report per campaign

- Sanitise template content on render. An admin-editable template that accepts arbitrary HTML is an injection vector into every client's inbox.

Exit criteria — do not start the next phase until all of these are true ☐ All eight transactional templates fire from real events with correct merge values ☐ Certificate delivery arrives with the PDF attached and opens correctly ☐ A failed send retries and lands in the dead-letter queue after exhausting attempts ☐ Bounce handling suppresses a known-bad address ☐ A campaign sends to a filtered set and reports delivery ☐ Template content cannot inject script into a rendered email

| PHASE 6 | Frontend migration | DURATION Weeks 5–10 | LEAD Partner |
| --- | --- | --- | --- |

The prototype is a single HTML file of roughly seven thousand lines. It is not the production frontend, but it is an exact specification of one: every screen, every modal, every validation message and every empty state has been reviewed and revised through several rounds of use.

Approach

- Rebuild as components in the chosen framework, screen by screen, matching the prototype

- Keep the visual language — it follows the Urbeno brand guidelines and uses the brand palette and typefaces

- Keep the copy. The labels, hints, warnings and refusal messages were written deliberately.

- Keep the mobile behaviour: the collapsing navigation, full-screen modals, scrolling tables, sixteen-pixel inputs

Screens to deliver

| Area | Screens |
| --- | --- |
| Shared | Login, password reset, profile, global search, notifications, terms of use footer |
| Admin | Dashboard with work queues, requests list and detail, masters (clients, sites, users, factories, categories, lookups, email), reports, Recycle Heroes, audit log |
| Factory | Dashboard, requests, MRN and recycling screens, capacity utilisation |
| Client | Site-wise dashboard, requests, new request, sustainability, Recycle Heroes, reports |

Things the prototype does that are easy to lose

- The lifecycle progress bar showing all nine stages with the current one marked

- Per-invoice tabs, because invoices progress independently after billing

- The derived stage badge appearing identically in lists, dashboards and the request page

- Live validation as it stands: the category split reconciling in real time, the material recovery seeded per category, the weight deviation prompting for a note only when it differs

- The single certificates panel at request level, listing certificates across all invoices

- Compliance documents grouped at the foot of the request

Exit criteria — do not start the next phase until all of these are true ☐ Every screen exists and is reachable for the role that owns it ☐ A full nine-stage lifecycle can be completed through the interface alone ☐ The interface is usable on a 390-pixel-wide screen with no horizontal page scrolling ☐ Validation messages match the prototype wording ☐ Client branding appears on the client portal alongside the Urbeno mark ☐ Accessibility audit passes WCAG 2.1 AA on client-facing screens

| PHASE 7 | Scheduled work | DURATION Weeks 8–10 | LEAD Partner |
| --- | --- | --- | --- |

Three recurring jobs, all modelled in the prototype. Each must be idempotent: running twice in a day must not send two emails.

| Job | Cadence | Behaviour |
| --- | --- | --- |
| Payment reminders | Daily | Finds invoices past their due date, derived from the client's agreed payment terms. Emails the client quoting the terms and how overdue the invoice is. Never chases a settled invoice. Records the send so a second run the same day does nothing. |
| Recycling SLA watch | Daily | Measures each invoice from its MRN receipt date against the thirty-day target. Raises an alert when it approaches or breaches. Alerts once per state change, not once per run. |
| Capacity alerts | Daily | Checks each facility's categories against its authorisation and alerts on eighty and one hundred per cent. |
| Retention sweep | Monthly | Deletes files and records past their retention window, and logs what was deleted. |
| Stage reconciliation | Daily | If a stored stage cache is kept, repairs drift and logs it. |

Operational requirements

- Use a real scheduler — the platform's cron, or a job runner with a queue. Not a timer inside the web process.

- Record each run: started, finished, records processed, errors

- Alert an operator if a job fails or does not run

- Every job must be runnable manually for testing, against a date the operator supplies

Exit criteria — do not start the next phase until all of these are true ☐ Each job runs on schedule and is visible in a run log ☐ Running a job twice in one day produces no duplicate emails ☐ Payment reminders respect each client's own agreed terms ☐ SLA alerts fire once per state change, not repeatedly ☐ A failed job raises an alert to a named person

| PHASE 8 | Reporting and analytics | DURATION Weeks 9–12 | LEAD Partner |
| --- | --- | --- | --- |

Eight reports, each available over four period bases and filterable by site, exporting to CSV and PDF.

| Report | Contains |
| --- | --- |
| Request summary | Every request with stage, weights and dates |
| Invoice register | Invoices with e-way bill, tax, payment status and outstanding |
| MRN register | Goods received by facility — staff only |
| Form 6 log | Processing records with categories |
| Certificate log | Certificates issued and closure status |
| Category recovery | Weight recovered against each authorised category |
| Sustainability | Environmental impact with methodology |
| Recycle Heroes | Tonnage and tree milestones |

Period handling

- Financial year (April to March), calendar year, a custom date range, or all time

- Site-wise filtering, plus a consolidated view for clients with several sites

- The same period logic as the rest of the system — one helper, used everywhere

Performance

- Reports must not be built by loading every record into memory. Aggregate in the database.

- Long exports run as background jobs with a download link when ready

- Index for the query patterns these reports use, and check the plans under realistic volume

Sustainability figures

Counted only from invoices where a certificate has been issued and the client has acknowledged closure. Conversion factors are documented in the methodology PDF and must be configurable, because the factors will be revised.

Exit criteria — do not start the next phase until all of these are true ☐ All eight reports return correct figures against a known data set ☐ Every period mode produces the right boundaries, including 31 March and 1 April ☐ Site filtering and consolidation both work for a multi-site client ☐ CSV and PDF export work for every report ☐ A report over 5,000 submissions returns within the agreed performance target ☐ Sustainability figures reconcile to the methodology document

| PHASE 9 | Security hardening and DPDPA | DURATION Weeks 10–13 | LEAD Partner + auditor |
| --- | --- | --- | --- |

This phase is routinely compressed when a deadline tightens. It should not be. The platform holds client personal data, commercial terms and compliance records, and Urbeno is accountable for all three.

Application security

- OWASP Top 10 review with findings recorded and closed

- Rate limiting on authentication, password reset, search and export

- Input validation on every endpoint; output encoding on every rendered value

- Security headers: HSTS, content security policy, frame options, referrer policy

- Dependency scanning in the pipeline, with a policy for how quickly a critical finding is patched

- No secrets in source, logs or error messages

Data protection under the DPDPA

- Consent captured at first login, with the version and timestamp recorded

- A privacy notice that names what is collected and why

- Data subject access and erasure processes, with a documented route for handling a request

- Breach notification procedure with named responsibilities and timelines

- Data residency confirmed and evidenced — nothing leaves India, including backups and logs

- A processing record listing every category of personal data held and its retention period

Third-party audit

- Independent penetration test, booked in Phase 0

- Findings triaged with owners and dates

- Critical and high findings closed before go-live; medium findings scheduled

- A retest confirming closure

The isolation test to insist on Ask the auditor specifically to attempt cross-tenant access: authenticated as one client, reach another client's submission, invoice, certificate or file by direct identifier and by manipulated request. This is the failure that would end a corporate contract, and it is the one worth paying to have tried properly.

Exit criteria — do not start the next phase until all of these are true ☐ Penetration test complete, with critical and high findings closed and retested ☐ Cross-tenant access attempts fail and are logged ☐ DPDPA documentation complete and reviewed by counsel ☐ Data residency evidenced for the database, object storage, backups and logs ☐ Dependency scanning runs in the pipeline with a patching policy ☐ An incident response procedure exists with named owners

| PHASE 10 | Data migration and UAT | DURATION Weeks 12–14 | LEAD Urbeno + Partner |
| --- | --- | --- | --- |

Two strands: getting real history in, and getting the people who will use it to confirm it works.

What to migrate

- Client and site master data, including GSTINs, addresses and payment terms

- Users, created without passwords — everyone sets their own through the reset flow

- Historical requests, to whatever depth Urbeno decides. Consider the last two financial years rather than everything.

- Historical compliance documents — Form 6, certificates, manifests — as files attached to the right records

- The tree planting ledger

Migration method

- Write a repeatable import script. Run it against staging as many times as needed.

- Validate after each run: record counts, weight totals, certificate numbers unique, no orphaned references

- Historical records that pre-date a field simply lack it. Do not invent values to fill columns.

- Derived stage means imported records report correctly without a stage column being set — one of the reasons that design matters.

User acceptance testing

Run in staging with the people who will actually use the system, not with the project team.

| Tester | Must complete |
| --- | --- |
| Operations coordinator | Acknowledge a request, assign two vehicles with teams, record both weighments including one manual, raise two invoices with different tax rates |
| Factory manager | Create MRNs at their facility, split a receipt across categories, confirm capacity warnings appear, upload processing evidence |
| Accounts | Record partial and full payments, confirm a request cannot close while unpaid, run the invoice register |
| Compliance officer | Retrieve Form 6, certificates and MRNs, run the certificate log, confirm retention |
| Sustainability lead | Download the sustainability certificate and Recycle Heroes report, reconcile to the methodology |
| A real client user | Raise a request, track it, receive the certificate email, close the request |

Training

- One session per role, recorded

- A short written guide per role, kept in the product

- A nominated superuser inside Urbeno who becomes the first line of support

Exit criteria — do not start the next phase until all of these are true ☐ Migration script runs clean against staging with validation passing ☐ Every UAT scenario above completed by the person who owns that role, with sign-off ☐ Defects from UAT triaged, and blockers fixed and retested ☐ Training delivered and recordings available ☐ At least one real client has used the staging system and given feedback

| PHASE 11 | Go-live | DURATION Weeks 14–15 | LEAD Urbeno + Partner |
| --- | --- | --- | --- |

Pick a quiet day. Not a Friday, not month end, not the week a large pickup is scheduled.

Before the day

- Production environment built and smoke-tested with a rehearsal migration

- DNS records prepared with a low time-to-live, set at least a day ahead

- Certificates issued and verified

- Monitoring, error tracking and alerting live and confirmed to page someone

- Backups running and a restore proven

- Rollback plan written, with the decision-maker and the trigger conditions named

- Clients told what is changing and when

On the day

1. Freeze changes in the old process 2. Final data migration run 3. Validation: counts, totals, spot checks against source 4. Smoke test production: login, raise a request, generate an MRN, upload a certificate, send an email, download a report 5. DNS cutover 6. Confirm mail is delivering from the production domain 7. Watch monitoring for the first two hours 8. Notify users that the system is live

The first week

- Daily check of error rates, job runs and email delivery

- A named engineer on call

- A fast route for users to report anything odd, and a daily triage of what comes in

- Do not deploy anything non-critical

Exit criteria — do not start the next phase until all of these are true ☐ Production serving real users on the live domain ☐ Migration validated against source records ☐ Monitoring and alerting confirmed working by a deliberate test ☐ Backups running with a proven restore ☐ A rollback plan exists and everyone knows who calls it ☐ No critical defects open

| PHASE 12 | Operate and hand over | DURATION Weeks 15–16 and beyond | LEAD Partner → Urbeno |
| --- | --- | --- | --- |

Handover

- Complete source in Urbeno's repository, with architecture documentation

- An operations runbook: how to restart, restore, add a user, rotate a secret, and diagnose the common failures

- A recorded handover session with the Urbeno technical owner

- Every credential transferred to Urbeno's password manager and the partner's access revoked or reduced

- A register of every third-party service, what it costs and who owns the account

Warranty

Ninety days from go-live, at the response times set out in the RFP: critical acknowledged within an hour and fixed within four; high within four hours and a day; medium within a business day and five days.

Ongoing costs to budget

| Item | At launch | At 24-month scale |
| --- | --- | --- |
| Hosting and database | ₹8,000–15,000 / month | ₹25,000–45,000 / month |
| Object storage | ₹500–1,500 | ₹3,000–8,000 |
| Email | ₹500–1,500 | ₹3,000–6,000 |
| SMS and WhatsApp | ₹2,000–5,000 | ₹10,000–25,000 |
| Monitoring and error tracking | ₹0–2,000 | ₹4,000–8,000 |
| Total | ₹11,000–25,000 / month | ₹45,000–90,000 / month |

A support retainer sits on top of this. The RFP suggests engaging the partner monthly for the first six months after warranty.

What to plan for next

- The driver progressive web app, deferred from the current scope

- EPR credit tracking, deferred pending Urbeno's own research

- CPCB portal integration, if and when an API becomes available

- Accounting integration with Tally or Zoho Books

- Hindi and Kannada interface, which the architecture should already allow for

Exit criteria — do not start the next phase until all of these are true ☐ Urbeno owns the code, the accounts and the credentials ☐ The runbook has been used by an Urbeno person to complete a real task ☐ Monitoring alerts reach Urbeno, not only the partner ☐ Warranty terms are agreed in writing ☐ The next phase of work is scoped, even if not commissioned

# Appendix A — Prototype to production mapping

Where each part of the prototype ends up. The prototype carries seventeen // MIGRATION: comments marking these points precisely.

| Prototype | Production | Note |
| --- | --- | --- |
| localStorage + saveState() | Postgres | Delete entirely. Persistence becomes the database. |
| db.subs, db.inv, db.veh | REST resources | One endpoint group per service object. |
| auth with SHA-256 | bcrypt or argon2 + server sessions | Prototype hashing is demo-grade and labelled as such. |
| audit.log() | Append-only table | Same payload shape. No update or delete permission. |
| notify.send() | Notifications table + push | In-app bell already modelled. |
| mail._deliver() | Email provider API | Template resolution and merge logic port unchanged. |
| files with data URIs | S3 with pre-signed URLs | Metadata stays in the database. |
| jsPDF in the browser | Server-side generation | Documents must be reproducible and job-generatable. |
| catm.utilization() | Aggregate query | Per facility, per fiscal year. |
| invStage() | View, generated column or shared function | Never a stored counter alone. |
| CATEGORY_MASTER_SEED | category_master table | 252 rows, 126 per facility. |
| backfillSeed() | Migration script | Repairs legacy shapes; delete once migration completes. |

# Appendix B — Test coverage to require

The prototype ships with 711 automated assertions across six suites. That is the standard to hold the production build to, and the suites are a ready-made specification of expected behaviour.

| Area | What must be tested |
| --- | --- |
| Lifecycle | All nine stages, in order, for single and multi-invoice requests |
| Validation refusals | Every rule that refuses: unbalanced split, missing photo, deviation without note, closure without payment, duplicate certificate number |
| Tenant isolation | Cross-client access attempts on every resource type |
| Role scoping | Client, site-scoped client, factory and admin against every endpoint |
| MRN sequencing | Concurrency, fiscal-year reset, per-facility isolation |
| Fiscal year | Boundary dates at 31 March and 1 April across reports, capacity and sequences |
| Capacity | Warning, block, override with reason, per-facility measurement |
| Derived stage | Every record shape, including legacy ones with stale counters |
| Money and weight | Arithmetic to the paisa and the kilogram, including tax derivation |
| Scheduled jobs | Idempotency — twice in a day sends once |
| Documents | Generation for every document type, including empty and maximal data |
| Reports | Every report against every period mode with known figures |

Ask for the test suite as a deliverable Tests are part of what Urbeno is buying, not a courtesy from the partner. Without them the second year of ownership becomes considerably more expensive, because nobody can change anything with confidence.

# Appendix C — Risks worth watching

| Risk | Signal | What to do |
| --- | --- | --- |
| Business rules rewritten from scratch rather than ported | The team asks for a written specification instead of reading the prototype | Insist on a walkthrough where they demonstrate the prototype rules in their build |
| Stage stored as a counter | A dashboard disagrees with a request when opened | Require the derived design; this defect already occurred once |
| MRN numbers colliding or skipping | Duplicates under load, or gaps in the register | Require a concurrency test as an acceptance condition |
| Security phase compressed | The audit slips to after go-live | Book and pay for the audit in Phase 0 so the date is fixed |
| Money in floating point | Totals off by a paisa in reports | Check the schema in Phase 1, before data exists |
| Mobile treated as an afterthought | Mobile work scheduled at the end | Require a mobile demonstration at the end of every frontend milestone |
| Migration left late | No migration script by Phase 10 | Require a rehearsal migration against staging in Phase 8 |
| Copy rewritten | Refusal messages become "Validation failed" | Review the messages during UAT — they are how an operator knows what to fix |

# Appendix D — Questions to ask at each milestone review

Phase 1

- Show me a change reaching production through the pipeline, with no manual step

- Show me the schema for money and for weights

Phase 2

- Sign in as a client and try to open another client's request by its identifier

- Show me the audit entry for the last thing you changed

Phase 3

- Take a request through all nine stages while I watch

- Show me what happens when the category split does not balance

- Show me two MRNs created at the same instant at the same facility

Phase 6

- Show me the whole lifecycle on a phone

Phase 9

- Show me the penetration test report and which findings are still open

Phase 10

- Show me the migration validation output

- Let my operations coordinator drive, unaided, while we watch

# Appendix E — The three problems most often got wrong

Everything else in this plan is ordinary engineering. These three are where a competent team can still produce something that looks right and is not. Each is given here as working SQL so there is no ambiguity about what is being asked for.

## 1 · Stage must be derived, never stored

The prototype originally stored a stage number on each record. It drifted the moment data was imported or edited outside the normal flow, and the dashboard then disagreed with the request when you opened it — which is exactly the fault you reported and I fixed in v6.3. Do not reintroduce it. Compute the stage from the records that actually exist.

CREATE VIEW invoice_stage AS SELECT i.id AS invoice_id, CASE WHEN i.closed_at IS NOT NULL THEN 9 WHEN EXISTS (SELECT 1 FROM certificates c WHERE c.invoice_id = i.id) THEN 8 WHEN EXISTS (SELECT 1 FROM recycling r WHERE r.invoice_id = i.id) THEN 7 WHEN EXISTS (SELECT 1 FROM mrns m WHERE m.invoice_id = i.id) THEN 6 ELSE 5 END AS stage FROM invoices i; -- A request sits at its least-advanced invoice, because it is only -- as finished as its slowest invoice. CREATE VIEW submission_stage AS SELECT s.id AS submission_id, COALESCE(MIN(v.stage), s.pre_billing_stage) AS stage FROM submissions s LEFT JOIN invoices i ON i.submission_id = s.id LEFT JOIN invoice_stage v ON v.invoice_id = i.id GROUP BY s.id, s.pre_billing_stage;

If the team insists on a stored column for query speed, it must be a generated column or maintained by trigger — never written by application code, and never the only source of truth.

## 2 · MRN numbering under concurrency

Two factory managers receiving material in the same second must not produce the same MRN number, and the register must have no gaps. Reading a counter and then writing it back — which is what the prototype does, correctly for a single user — will eventually issue duplicates on a real server.

CREATE TABLE mrn_counters ( factory_code TEXT NOT NULL, fy TEXT NOT NULL, -- 2526 for FY 2025-26 last_value INT NOT NULL DEFAULT 0, PRIMARY KEY (factory_code, fy) ); -- Allocation is one statement, so concurrent callers queue rather than race. -- Run it inside the same transaction that inserts the MRN row. INSERT INTO mrn_counters AS c (factory_code, fy, last_value) VALUES ($1, $2, 1) ON CONFLICT (factory_code, fy) DO UPDATE SET last_value = c.last_value + 1 RETURNING last_value; -- Second line of defence: the number itself cannot repeat ALTER TABLE mrns ADD CONSTRAINT mrn_no_unique UNIQUE (mrn_no);

Acceptance test: fire fifty simultaneous MRN creations at one factory and assert fifty distinct, consecutive numbers with no gaps. Ask to see this run.

## 3 · Tenant isolation in the database, not only the application

If client separation lives only in application code, one forgotten condition in one endpoint exposes another client's data. Row-level security makes that mistake much harder to make and much easier to catch.

ALTER TABLE submissions ENABLE ROW LEVEL SECURITY; -- Staff see everything CREATE POLICY staff_all ON submissions USING (current_setting('app.role', true) IN ('admin','factory')); -- Client users see their own organisation, restricted to their sites CREATE POLICY client_own ON submissions USING ( current_setting('app.role', true) = 'client' AND client_code = current_setting('app.client_code', true) AND ( current_setting('app.site_scope', true) = '' OR site_id = ANY (string_to_array( current_setting('app.site_scope', true), ',')) ) ); -- Set once per request, from the verified session — never from user input SET LOCAL app.role = 'client'; SET LOCAL app.client_code = 'TCPL'; SET LOCAL app.site_scope = 'BLR';

Two smaller things that are cheap now and expensive later Money in NUMERIC(14,2), never a floating-point type. Floating point will put invoice totals a paisa out in reports and nobody will find it for months. Weights in NUMERIC(12,3) — you weigh to the kilogram but recovery splits carry decimals, and rounding drift breaks the rule that a category split must total the invoice weight exactly.

— End of build plan —